## Project Overview
Project Information | Details
Project Name | Manual Testing of AcademyBugs
Tester | Gibran Napier
Project Status | Completed
Application Under Test | AcademyBugs
Testing Types | Functional and exploratory testing using positive, negative, and boundary-value techniques
Device | Chromebook
Operating System | ChromeOS
Browser | Google Chrome
Browser Version | Version 151.0.7922.168 (Official Build) (64-bit)
Start Date | 2026-09-04
Objective | Evaluate the website’s core e-commerce functionality, identify defects, document reproducible evidence, and communicate testing results clearly.
Scope | Product browsing, product details, product search, product sorting, cart behavior, empty-cart navigation, checkout navigation, required-field validation, and interface observations.
Out of Scope | Payment processing, security testing, performance testing, and administrative functionality.

## Test Cases
Test Case ID | Feature | Test Case Title | Test Type | Priority | Preconditions | Test Data | Test Steps | Expected Result | Actual Result | Status | Defect ID | Screenshot Evidence | Video Evidence | Execution Date | Tester Notes
TC-001 | Product Details | Verify a selected product’s details page displays correct product information | Functional | High | The AcademyBugs website is accessible, cookie consent has been accepted, and the product catalog is open. | Product: DNK Yellow Shoes | 1. Open the AcademyBugs products page. 2. Select a product. 3. Observe the resulting product-details page. | The correct product-details page opens and displays the selected product’s correct name, image, price, and a meaningful English description. | The DNK Yellow Shoes product-details page opened with the correct product name, image, and price. However, the description displayed Lorem Ipsum placeholder text instead of a meaningful English product description. | Fail | DEF-001 | View Description Defect |  | 2026-09-04 | Placeholder content prevents users from receiving a meaningful product description.
TC-002 | Shopping Cart | Verify adding one product to the cart displays the correct item and totals | Functional | High | AcademyBugs Find Bugs page is accessible, cookie consent is accepted, and the cart is empty | DNK Yellow Shoes; Quantity: 1 | 1. Open DNK Yellow Shoes. 2. Confirm the quantity is set to 1. 3. Click Add to Cart. 4. Observe the shopping-cart page and review the cart contents and totals. | One DNK Yellow Shoes product is added to the cart with the correct name, image, price of $45.00, quantity of 1, and calculated total. | Clicking Add to Cart opened the shopping-cart page and added one DNK Yellow Shoes item with the correct $45.00 price and quantity of 1. The $45.00 subtotal and $7.99 shipping charge displayed correctly, but the grand total displayed as $152.99 instead of the expected $52.99. | Fail | DEF-002 | View Incorrect Total- Qty 1 |  | 2026-09-04 | Product addition succeeded, but total validation failed. See DEF-002.
TC-003 | Shopping Cart | Verify changing product quantity recalculates cart totals | Functional | High | One DNK Yellow Shoes item is displayed in the shopping cart with a quantity of 1. | DNK Yellow Shoes; Quantity changed from 1 to 2 | 1. Increase the quantity to 2. 2. Click Update. 3. Review the displayed quantity, item total, subtotal, shipping charge, and grand total. | The quantity displays as 2. The item total and subtotal become $90.00. With a $7.99 shipping charge, the grand total becomes $97.99. | After the quantity was increased from 1 to 2 and Update was selected, the item total and cart subtotal correctly changed to $90.00. Shipping remained $7.99, but the grand total displayed as $197.99 instead of the correct $97.99. | Fail | DEF-002 | View Incorrect Total - Qty 2 | View Incorrect Total - Qty 2 (video) | 2026-09-04 | The existing grand-total defect persists after changing the product quantity.
TC-004 | Shopping Cart | Verify a product can be removed from the shopping cart | Functional | High | DNK Yellow Shoes is present in the shopping cart | DNK Yellow Shoes | 1. Open the shopping cart. 2. Click the gray remove control beside DNK Yellow Shoes. 3. Observe the cart contents, totals, and empty-cart state. | DNK Yellow Shoes is removed. The cart displays an empty-cart state, no product remains listed, and the previous subtotal and grand total are cleared. | Clicking the remove control displayed a temporary loading indicator and successfully removed DNK Yellow Shoes. The cart then displayed an empty-cart message, and the previous item, totals, and checkout controls were cleared. A separate content defect was observed in the Return to Store button label. | Pass |  | View Empty-Cart Result | View Cart Removal Process (video) | 2026-09-04 | Removal functionality passed; DEF-003 was observed in the resulting empty-cart state.
TC-005 | Empty Cart Navigation | Verify Return to Store button returns the user to the product catalog | Functional | Medium | The shopping cart is empty and the empty-cart page is displayed | Not applicable | 1. Confirm the empty-cart page is displayed. 2. Click Return to Store. 3. Observe the destination page. | The button opens the product catalog, and available products display successfully without an error. | Clicking Return to Store opened the product catalog successfully. The URL changed appropriately, available products displayed, and no application error appeared. The AcademyBugs training prompt appeared as part of the testing environment. | Pass |  | View Product-Catalog Result |  | 2026-09-04 | Navigation function passed. The separate button-label content defect is documented as DEF-003.
TC-006 | Product Search | Verify searching for an existing product returns a relevant result | Functional | High | A product-details page is loaded, and the Product Search field and Search button are visible and enabled. | DNK Yellow Shoes | 1. Locate the Product Search field. 2. Enter “DNK Yellow Shoes”. 3. Click Search. 4. Review the displayed results. | The search completes without an error and displays DNK Yellow Shoes as a relevant result. Unrelated products should not appear. | Searching for “DNK Yellow Shoes” by pressing Enter and by clicking Search returned two products: DNK Yellow Shoes and Blue Hoodie. DNK Yellow Shoes appeared as expected. Blue Hoodie also displayed DNK branding on the product image, indicating relevance to the “DNK” search term. No error occurred. | Pass |  | View Product Search Result | View Product Search Result (video) | 2026-09-05 | Blue Hoodie displayed DNK branding and was treated as potentially relevant to the query. The exact product attributes indexed by search are not documented. The search field’s placement is retained as a usability observation, not a confirmed defect.
TC-007 | Product Search | Verify no products are returned for a nonexistent product search | Functional | Medium | A product-details page is loaded, and the Product Search field and Search button are visible and enabled. | Search term: NoSuchProduct98765 | 1. Click the Product Search field. 2. Enter “NoSuchProduct98765”. 3. Click the Search button. 4. Observe the displayed search results and any accompanying message. | The search should complete successfully without displaying any products. A clear message should inform the user that no matching products were found, and no application error should occur. | The search completed successfully and displayed no products. The page showed the message “No results found,” and no application error occurred. | Pass |  | View Nonexistent Product Search Result |  | 2026-09-05 | Negative search input was handled successfully with a clear zero-results state.
TC-008 | Shopping Cart | Verify the cart accepts the maximum purchase quantity of 10 | Functional | Medium | The DNK Yellow Shoes product-details page is loaded. The product is in stock with at least 11 units available, the cart is empty, and the quantity controls are visible and enabled. The page displays a maximum purchase quantity of 10. | Product: DNK Yellow Shoes; Starting quantity: 1; Stated maximum quantity: 10; Test quantity: 10 | 1. Confirm that the DNK Yellow Shoes product-details page displays a maximum purchase quantity of 10. 2. Use the quantity-increase control to change the quantity from 1 to 10. 3. Click Add to Cart. 4. Observe the shopping-cart page. 5. Review the displayed product name and quantity. | DNK Yellow Shoes should be added to the shopping cart with a displayed quantity of 10. The application should not reject, reduce, or modify the quantity, and no maximum-limit error should appear. | After Add to Cart was selected, the shopping-cart page displayed DNK Yellow Shoes with a quantity of 10. The quantity was not rejected, reduced, or modified, and no maximum-limit error appeared. | Pass |  | View Cart Quantity Limit | View Cart Quantity Limit (video) | 2026-09-05 | The valid upper-boundary quantity of 10 was accepted successfully.
TC-009 | Shopping Cart | Verify the quantity cannot exceed the maximum purchase limit of 10 | Functional | Medium | The DNK Yellow Shoes product-details page is loaded. The cart is empty, the quantity controls are visible and enabled, and the page displays a maximum purchase quantity of 10. | Product: DNK Yellow Shoes; Starting quantity: 1; Maximum quantity: 10; Invalid test quantity: 11 | 1. Confirm that the product page states a maximum purchase quantity of 10. 2. Use the quantity-increase control to change the quantity from 1 to 10. 3. Attempt to increase the quantity from 10 to 11. 4. Observe the displayed quantity and any validation message. 5. If the page permits a displayed quantity of 11, click Add to Cart and inspect the quantity added to the cart. | The application should prevent a quantity of 11 from being selected or added to the cart. The quantity should remain at the maximum of 10, or the application should reject the invalid quantity with a clear validation message. | The quantity was increased to 11, and the application displayed the validation message “Maximum purchase amount of 10 is allowed.” The application prevented 11 units from being added to the shopping cart. | Pass |  | View Maximum-Quantity Validation |  | 2026-09-05 | The invalid boundary value of 11 triggered the expected validation message, and the maximum purchase limit was successfully enforced.
TC-010 | Product Sorting | Verify Price Low-High arranges products in ascending order | Functional | Medium | The product catalog is loaded, multiple products and their prices are displayed, and the sorting dropdown is visible and enabled with Price Low-High available. | Sorting option: Price Low-High; Products displayed before sorting: 18 | 1. Open the product catalog. 2. Confirm that all 18 products are displayed. 3. Open the Default Sorting dropdown. 4. Select Price Low-High. 5. Confirm that all 18 products remain displayed. 6. Review the products from left to right and then from top to bottom. 7. Compare each publicly displayed numerical price with the preceding price. 8. Observe whether an application error or other unexpected behavior occurs. | All 18 products should remain displayed. Products with publicly displayed numerical prices should be arranged from the lowest price to the highest price when read from left to right and then from top to bottom. Each numerical price should be equal to or greater than the preceding numerical price. Products without publicly displayed prices should remain in the catalog without causing an application error. | After Price Low-High was selected, all 18 products remained in the catalog. Products with publicly displayed numerical prices were arranged in ascending order when read from left to right and top to bottom. Current sale prices were used for discounted products, and no application error occurred. | Pass |  |  | View Price-Sorting Validation | 2026-09-05 | Dark Blue Denim Jeans displayed “Login for Pricing,” so its position could not be independently verified against a publicly displayed numerical price. All other visible numerical prices followed ascending order.
TC-011 | Checkout | Verify selecting Checkout from a populated cart opens the checkout-details page and preserves visible order information | Functional | High | The shopping-cart page is loaded with DNK Yellow Shoes at a quantity of 1. The Checkout button is visible and enabled. | Product: DNK Yellow Shoes; Quantity: 1; Unit price: $45.00 | 1. Confirm that the shopping cart displays DNK Yellow Shoes with a quantity of 1 and a unit price of $45.00. 2. Click Checkout. 3. Confirm that the Checkout Details page opens. 4. Review the available customer and billing-information fields. 5. Review the Your Cart section. 6. Compare the displayed product name and price with the values previously displayed in the shopping cart. 7. Observe whether an application error occurs. | The Checkout Details page should open successfully and display returning-customer and billing-information options. The Your Cart section should preserve DNK Yellow Shoes and its $45.00 price. No product information should be unexpectedly changed or lost, and no application error should occur. | Clicking Checkout opened the Checkout Details page successfully. The page displayed returning-customer and billing-information options. The Your Cart section retained DNK Yellow Shoes at $45.00, matching the product and price displayed in the shopping cart. No application error occurred. | Pass |  |  | View Checkout Navigation Results | 2026-09-06 | The checkout page retained the product name and $45.00 price. Quantity was not displayed separately, so it could not be independently verified from the checkout page. No new defect was identified.
TC-012 | Checkout | Verify checkout prevents continuation when required billing fields are blank | Functional | High | The Checkout Details page is loaded with DNK Yellow Shoes displayed in the cart at $45.00. The billing-information form and Continue to Shipping button are visible and enabled. | Country: unselected; Required billing text fields: blank; Product: DNK Yellow Shoes; Displayed price: $45.00 | 1. Confirm that Country has not been selected and all required billing text fields are blank. 2. Click Continue to Shipping. 3. Observe the validation feedback associated with the missing required information. 4. Confirm whether the user remains on the Checkout Details page or proceeds to shipping. 5. Confirm that DNK Yellow Shoes and its $45.00 price remain displayed. 6. Observe whether an application error or other unexpected behavior occurs. 7. As a focused retest, populate the required fields with valid-looking test data while leaving Retype Email blank. 8. Click Continue to Shipping and observe the Retype Email validation response. | The application should prevent progression to shipping and keep the user on the Checkout Details page when required information is missing. Clear validation feedback should identify the missing or invalid information necessary to continue. DNK Yellow Shoes and its $45.00 price should remain displayed, and no application error should occur. | Clicking Continue to Shipping with required checkout information missing prevented progression and kept the user on the Checkout Details page. The application displayed field-specific validation feedback for the missing required information and the general message “Please correct the errors in your checkout details.” A focused retest with Email populated and Retype Email blank displayed “Your email addresses do not match” and again prevented progression. DNK Yellow Shoes remained in the checkout flow, and no application error occurred. | Pass |  |  | View Required-Field Validation Evidence |  | Retype Email validation is conditional on the primary Email field containing a value. The focused retest confirmed that Retype Email is validated and that incomplete checkout information cannot proceed to shipping. No defect was confirmed.

## Defect Reports
Defect ID | Defect Title | Related Test Case | Feature | Issue Type | Environment | Severity | Priority | Preconditions | Steps to Reproduce | Expected Result | Actual Result | Reproducibility | Screenshot Evidence | Video Evidence | Status | Date Reported | Additional Notes
DEF-001 | DNK Yellow Shoes displays Lorem Ipsum placeholder text in product description | TC-001 | Product Details | Content | Chromebook / ChromeOS / Chrome 151.0.7922.168 | Medium | Medium | AcademyBugs Find Bugs page is open and cookie consent has been accepted | 1. Open the Find Bugs page. 2. Select “DNK Yellow Shoes.” 3. Review the product description. | The product-details page should display a meaningful English description of DNK Yellow Shoes, consistent with the website’s English interface. | The product-details page consistently displays Lorem Ipsum placeholder text instead of a meaningful English product description. The issue remained after refreshing the page and repeating the test. | Always | View Description Defect |  | New | 2026-09-04
DEF-002 | Shopping cart grand total is calculated $100 too high | TC-002 | Shopping Cart | Functional | Chromebook / ChromeOS / Chrome 151.0.7922.168 | High | High | Cart is empty and DNK Yellow Shoes is available for $45.00 | 1. Open DNK Yellow Shoes. 2. Set quantity to 1. 3. Click Add to Cart. 4. Review the cart totals. | The $45.00 subtotal plus $7.99 shipping should produce a grand total of $52.99. | The subtotal and shipping display correctly, but the grand total displays as $152.99—$100 above the correct total. | Always | View Incorrect Total- Qty 1 | View Grand-Total Recalculation (video) | New | 2026-09-04 | The issue also reproduced after changing the quantity to 2. With a $90.00 subtotal and $7.99 shipping, the grand total displayed as $197.99 instead of $97.99. Both executions added an unexplained $100.00 to the correct total.
DEF-003 | Return to Store button incorrect spacing before final letter | TC-004 | Empty Cart | Content | Chromebook / ChromeOS / Chrome 151.0.7922.168 | Low | Low | Shopping cart contains at least one product | 1. Open the shopping cart. 2. Remove the remaining product. 3. Observe the Return to Store button on the empty-cart page. | The button should display "Return to Store" with consistent spacing and alignment. | An excessive space appears before the final “E” in “STORE,” causing the button caption to display as “RETURN TO STOR E.” | Always | View Button-Label Defect | View Button-Label Defect (video) | New | 2026-09-04 | AcademyBugs’ built-in review identified the issue type as Content.

## Test Summary
Summary Metric | Details
Project Name | Manual Testing of AcademyBugs
Test Cycle | Cycle 1 – Initial Functional Testing
Testing Period | September 4–6, 2026
Environment | Chromebook / ChromeOS / Google Chrome 151.0.7922.168 (64-bit)
Total Test Cases | 12
Passed | 9
Failed | 3
Blocked | 0
Not Run | 0
Pass Rate | 75%
Total Defects | 3
Critical Defects | 0
High-Severity Defects | 1
Medium-Severity Defects | 1
Low-Severity Defects | 1
Overall Assessment | Twelve test cases were executed against AcademyBugs, resulting in nine passes, three failures, and a 75% pass rate. Within the tested scope, the core product-browsing, search, cart, sorting, and checkout workflows generally functioned; however, DEF-002 presents a significant financial risk because the shopping-cart grand total could overcharge customers. In a production e-commerce environment, the tested build would require correction and verification of the grand-total calculation before release.
Known Risks | The unresolved grand-total calculation defect creates a financial risk because customers could be charged an incorrect amount. Placeholder product content may reduce purchasing confidence, while the Return to Store spacing defect lowers interface quality. Compatibility outside Chrome on ChromeOS remains unverified, and payment processing, security, performance, and administrative functionality were excluded from this test cycle.
Recommended Next Steps | The highest-priority action is to investigate and correct the grand-total calculation defect across multiple products, quantities, and cart combinations. After correction, DEF-002 should be retested using its original reproduction steps, followed by regression testing of cart updates, shipping charges, and checkout totals. The lower-severity content defects should also be corrected and verified. Future test cycles should cover returning-customer login, completion of valid checkout details, shipping progression, additional browsers and devices, and the areas excluded from this test cycle.